## User Stories
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Create user stories list | 2024-03-14 | 2024-03-15
2 | Finish Task breakdown | 2024-03-18 | 2024-03-18
3 | Create Design Guide | 2024-03-18 | 2024-03-18
4 | Create a Design for the Website Using Figma | 2024-03-18 | 2024-03-18
5 | Write Source Code for the Home Page | 2024-03-18 | 2024-03-18
6 | Find a list of JS Functions to implement | 2024-03-19 | 2024-03-19
7 | Write the Contact Form for the Website | 2024-03-22 | 2024-03-22
8 | Add all pictures and video | 2024-03-23 | 2024-03-30
9 | Finetune overall design to match what I want exactly | 2024-03-24 | 2024-03-30
10 | Finish Up on website | 2024-03-25 | 2024-03-30
11 | User testing | 2024-03-27 | 2024-04-01
12 | Implement changes found through Testing | 2024-03-28 | 2024-04-02
13 | Submit | 2024-03-30 | 2024-04-02
14
15
...